## Table 1
Phase | Module Name | Task Name | Category | Description | Dependencies/Requirements | Implementation Priority | Source
Phase 0 | Authentication | Task P0.1 | Backend/API | Implement signup, login, OTP, password management, session/token handling, user creation, and database connection. | Database connection established | Highest (Done) | 1
Phase 1 | Business Foundation | Task 1 | Database Model | Design the business database model to store vendor business identity. | Authentication complete | Immediate Next | 1
Phase 1 | Business Foundation | Task 2-4 | API | Create, Get, and Update APIs for business entities. | Business database model | High | 1
Phase 1 | Business Foundation | Task 5 | Frontend | Develop the business setup wizard for onboarding vendors (initially targeting Retail/Kirana). | Business APIs | High | 1
Phase 1 | Business Foundation | Task 6 | Logic/API | Connect the authenticated user to the created business entity. | Auth and Business models | High | 1
Phase 2 | Product Foundation | Task 7-8 | Database Model | Create database models for Categories and Products. | Business Foundation | Medium-High | 1
Phase 2 | Product Foundation | Task 9-12 | API | Develop APIs for Create, Update, Delete/Archive, and List products. | Product models | Medium-High | 1
Phase 3 | Inventory | Task 15-16 | Database Model | Design Inventory and Inventory Transaction models. Architectural rule: never overwrite inventory directly; track movement. | Product Foundation | Medium | 1
Phase 3 | Inventory | Task 22 | Logic/Intelligence | Implement low-stock detection (initial component of the Business Brain). | Inventory models | Medium | 1
Phase 4 | Sales | Task 23-25 | API/Database | Create Sale and Sale Items models and corresponding creation APIs. | Inventory and Products | Medium | 1
Phase 4 | Sales | Task 26 | Logic/Automation | Implement automatic deduction of inventory upon sale recording. | Sale API and Inventory Module | Medium | 1
Phase 4 | Sales | Task 27 | Invoice Engine | Develop engine for generation of invoices with statuses (Draft, Final, Cancelled). | Sale API | Medium | 1
Phase 5 | Customers | Task 33-34 | Customer Ledger | Track customer ledger and outstanding balances (Business Brain calculation). | Sales Module | Medium | 1
Phase 9 | Financial Engine | Task 52-56 | Logic/Intelligence | Calculate financial metrics: Revenue, COGS, Gross Profit, Operating Expenses, and Net Profit. | Sales, Purchases, and Expense Modules | Medium-Low | 1
Phase 11 | Rules Engine | Task 67-72 | Deterministic Intelligence | Implement non-AI rules for low-stock, overdue customers, slow-moving inventory, and sales/margin declines. | Financial Engine and Transaction data | Low | 1
Phase 12 | Business Brain V1 | Task 73-77 | Intelligence UI | Build insights and recommendation models based on priority scores and impact calculations. | Rules Engine | Low | 1
Phase 14 | AI V1 | Task 83-87 | AI Architecture | Introduce LLM via AI service layer; provides structured explanations for business data (Ask VendorOS). | Business Brain V1 and Transactional Truth | Future | 1
Phase 17 | WhatsApp | Task 98-103 | Interface/Channel | Integration for message ingestion, order extraction, and sending invoices/reminders. | Action Engine and AI Context | Future | 1
Phase 19 | Offline Architecture | Task 108-112 | Architecture | Implement local database and sync engine to allow operation without internet. | Data models must be offline-safe | Future | 1

## Source References
Index | Reference
1 | Haan. Ab humein **“feature list” se project archi…